## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43

## 20%2024-utilization
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | MIMAROPA |  | CALENDAR YEAR: | 2024
PROVINCE: | ROMBLON |  | QUARTER: | First Quarter
CITY/MUNICIPALITY: | SANTA FE
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Counterpart Fund to National PPAs |  | 1178586 | 2023-01-01 | 2023-12-31 | 0%
Purchase of Land |  | 1500000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Construction of Agmanic Shoreline Protection (Sitio Bulucawe-Sitio Canyugan) | Agmanic | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation/Improvrment of Guintigbasan Seawall(Sitio Punta)Phase III | Guintigbasan | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Danao Norte Local Access Road (Purok Progreso) Phase V | Danao Norte | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Guinbirayan Local Access Road (Purok Bagong Buhay) Phase I | Guinbirayan | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Mat-I Local Access Road (Sitio Bulagsong) Phase IV | Mat-i | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Pandan Local Access Road (Sitio Kapinayan) | Pandan | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Poblacion Local Access Road (Sitio Longa-Og) | Poblacion | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation of Tabugon Local Access Road (Purok Masikap) Phase III | Tabugon | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation/ Improvement of Canyayo Multi-Purpose Hall(Phase IV) | Canyayo | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation/Improvement of Danao Sur Multi-Purpose Buildings(Phase III) | Danao Sur | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Construction of Multi-Purpose Hall(Magsaysay Elementary School) | Magsaysay | 600000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation/Improvement of Longaog Acces Road Leading to Municipal Slaughterhouse |  | 1800000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Rehabilitation/Improvement of Sambiray Acces Road Leading to Sanitary Landfill |  | 3500000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
[5 empty] | 0 | 0 |  | Not yet Started
Equipping of Santa Fe Women Development and Livelihood Center |  | 700000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
Establishment and Operation of Sanitary Landfill(Phase II) |  | 6000000 | 2023-01-01 | 2023-12-31 | 0% | 0 |  | Not yet Started
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
CARMEL P. PANAGSAGAN |  |  |  |  | ELSIE D. VISCA
Local Budget Officer |  |  |  |  | Local Chief Executive