## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | MIMAROPA |  | CALENDAR YEAR: | 2023
PROVINCE: | ROMBLON |  | QUARTER: | 4
CITY/MUNICIPALITY: | SANTA FE
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date | [7 empty] | % of Completion | Total Cost Incurred to Date
[9 empty] | LGSF-GEF Construction of Slaughterhouse | Santa Fe | 5873450 | 2022-09-08 | 2023-07-10 | 0% | 0
LGSF-GEF Construction of Slaughterhouse | Santa Fe | 5873450 | 2022-09-08 | 2023-07-10 | =G12/C12 | 5873450 |  |  | Additional financial assistance for FY 2021, EMB IV Mimaropa Improvement of material recovery facility | Santa Fe | 200000 | 2021-01-10 | 12/31/2022 | =Q12/M12 | 199048.8 |  | 951.2 to be returned to source agency
Additional financial assistance for FY 2021, EMB IV Mimaropa Improvement of material recovery facility | Santa Fe | 200000 | 2021-01-10 | 12/31/2022 | =G13/C13 | 200000 |  | 951.2 already returned to source agency | 12th Cycle Supplementary feeding program | Santa Fe | 1063800 | 2022-03-10 | 4/30/2023 | =Q13/M13 | 1063800
DSWD-Social Pension for Indigent Senior Citizen for 2nd semester CY 2023 | Santa Fe | 5721000 | 2023-10-08 | 12/31/2023 | =G14/C14 | 5721000 |  | unexpended amount of 159,000 returned to source agency
DOH CHD MIMAROPA- Health Emergency allowance for the Month of July to Dec 2021 | Santa Fe | 1557000 | 2023-11-09 | 10/31/2023 | =G15/C15 | 1557000 |  | unexpended amount of 9,000 returned to source agency
DOH CHD MIMAROPA - Equipping of Sta Fe Health Facilities in Danao Norte, Mat-I, Pandan, Tabugon NHS and Santa Fe RHU | Danao Norte, Mat-I, Pandan, Tabugon NHS and Santa Fe RHU | 3260000 | 12/2023 | 4/30/2024 |  | 0 |  | on going procurement process
DOH CHD MIMAROPA - 1st tranche (20%) Completion, repair and upgrading of Guinbirayan BHS | Santa Fe | 200000 | 12/2023 | 5/15/2024 |  | 0 |  | on going procurement process
DSWD-13th cycle Supplementary feeding program | Santa Fe | 1386000 | 2024-12-02 | 5/31/2024 |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CARMEL P. PANAGSAGAN |  |  | MARY GRACE D. DELOS REYES |  |  | ELSIE D. VISCA
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
38